## Daily Scrum
Daily Scrum
Start date | Subject | Task | Status | Time | Comment | Sprint
2026-01-19 | Yohanes | In-class Activity (User Stories) | Done | 1 hr |  | Sprint 1 [System Requirements (Jan 19 - Feb 2, 2026)] : Project planning and requirements gathering. The team completed in-class user story activities, defined system requirements for all 8 features, wrote domain and non-functional requirements, built use-case/sequence/activity diagrams, created traceability matrices, and wrote acceptance criteria.
| Yehezkiel | In-class Activity (User Stories) | Done | 1 hr
| Edgar | In-class Activity (User Stories) | Done | 1 hr
| Ansella | In-class Activity (User Stories) | Done | 1 hr
2026-01-20 | Yehezkiel | Feature 6 System Requirements | Done | 1 hr
| Ansella | Feature 1 & 3 System Requirements and User Stories | Done | 3 hrs
| Yohanes | Project Description | Done | 30 mins
| Yohanes | Feature 4 System Requirements and User Stories | Done | 2 hrs
| Edgar | Feature 2 System Requirements | Done | 30 mins
2026-01-21 | Yehezkiel | Feature 8 System Requirements | Done | 1 hr
| Ansella | Domain Requirements | Done | 1 hr
| Yohanes | Feature 7 System Requirements | Done | 30 mins
| Edgar | Feature 5 System Requirements | Done | 30 mins
2026-01-22 | Ansella | Domain Requirements | Done | 1 hr
| Yehezkiel | Feature 6 User Stories | Done | 1 hr
| Yohanes | Feature 7 User Stories | Done | 30 mins
| Edgar | Feature 5 System Requirements | Done | 45 mins
2026-01-23 | Ansella | Setting up Github for the project | Done | 1 hr
| Edgar | Non-functional Requirements | Done | 1 hr
2026-01-24 | Yehezkiel | Feature 8 User Stories and Project Goal | Done | 1.5 hrs
2026-01-25 | Ansella | Discussed Next Steps in M1 | Done | 1.5 hrs
| Edgar | Discussed Next Steps in M1 | Done | 1.5 hrs
| Yehezkiel | Discussed Next Steps in M1 | Done | 1.5 hrs
| Yohanes | Discussed Next Steps in M1 | Done | 1.5 hrs
| Yehezkiel | Refined SSR and US for Feature 6 | Done | 3 hrs
2026-01-26 | Yehezkiel | Refined SSR and US for Feature 8 | Done | 2 hrs
| Edgar | Refined SSR and US for Feature 2 and 5 | Done | 4 hrs
| Ansella | Refined SSR and US for Feature 1 and 3 | Done | 4 hrs
| Yohanes | Refined SSR and US for Feature 4 and 7 | Done | 5 hrs
| Ansella | Discussed Next Steps in M1 | Done | 2 hrs
| Edgar | Discussed Next Steps in M1 | Done | 2 hrs
| Yehezkiel | Discussed Next Steps in M1 | Done | 2 hrs
| Yohanes | Discussed Next Steps in M1 | Done | 2 hrs
2026-01-27 | Ansella | Made Traceability Matrix for Feature 1 and 3 | Done | 1 hr
| Edgar | Made Traceability Matrix for Feature 2 and 5 | Done | 1 hr
| Yehezkiel | Made Traceability Matrix for Feature 6 and 8 | Done | 1 hr
| Yohanes | Made Traceability Matrix for Feature 4 and 7 | Done | 1 hr
2026-01-28 | Edgar | Acceptance Criteria for Feature 2 and 5 | Done | 2 hr
| Ansella | Acceptance Criteria for Feature 1 and 3 | Done | 2 hr
| Yehezkiel | Acceptance Criteria for Feature 6 and 8 | Done | 2 hr
| Yohanes | Acceptance Criteria for Feature 4 and 7 | Done | 2 hr
| Yohanes | Created Pre-Lab Use-Case Diagram | Done | 1 hr
| Ansella | Created Pre-Lab Sequence Diagram | Done | 1 hr
2026-01-29 | Yohanes | Revised Pre-Lab Use-Case Diagram | Done | 30 mins
| Yehezkiel | Created Pre-Lab Activity Diagram | Done | 1 hr
| Edgar | Created Pre-Lab Activity Diagram | Done | 1 hr
| Ansella | Individual Reflection M1 | Done | 2 hr
2026-01-30 | Ansella | Reorganizing priority in GIthub Backlog | Done | 15 mins
| Edgar | Reorganizing priority in GIthub Backlog | Done | 15 mins
2026-02-03 | Ansella | Discussed Next Steps in M2 | Done | 15 mins |  | Sprint 2 [System architecture and design (Feb 3 - Feb 17, 2026)] : The team discussed M2 next steps, created sequence diagrams (account creation, add to cart), identified components and connections, produced a Level 1 Data Flow Diagram, and completed the unit testing lab activity.
| Edgar | Discussed Next Steps in M2 | Done | 15 mins
| Yehezkiel | Discussed Next Steps in M2 | Done | 15 mins
| Yohanes | Discussed Next Steps in M2 | Done | 15 mins
2026-02-04 | Ansella | Created Account Creation Sequence Diagram for M2 | Done | 1 hr
2026-02-05 | Ansella | Created Add to Cart Sequence Diagram for M2 | Done | 1 hr
2026-02-06 | Edgar | Identifying Component along with Its Connection | Done | 2 hr
2026-02-08 | Ansella | Discussed Next Steps in M2 | Done | 2 hr
| Edgar | Discussed Next Steps in M2 | Done | 2 hr
| Yehezkiel | Discussed Next Steps in M2 | Done | 2 hr
| Yohanes | Discussed Next Steps in M2 | Done | 2 hr
2026-02-11 | Yehezkiel | Created Level 1 Data Flow Diagram | Done | 3 hr
2026-02-12 | Yehezkiel | Revised Level 1 Data Flow Diagram | Done | 3 hr
| Yehezkiel | Identified and Logged Components for Feature 6 & 8 in Traceability Matrix | Done | 30 mins
| Ansella | Identified and Logged Components for Feature 1 & 3 in Traceability Matrix | Done | 30 mins
| Edgar | Identified and Logged Components for Feature 2 & 5 in Traceability Matrix | Done | 30 mins
| Yohanes | Identified and Logged Components for Feature 4 & 7 in Traceability Matrix | Done | 30 mins
2026-02-13 | Ansella | Unit Testing Lab Activity | Done | 30 mins
| Edgar | Unit Testing Lab Activity | Done | 30 mins
| Yehezkiel | Unit Testing Lab Activity | Done | 30 mins
| Yohanes | Unit Testing Lab Activity | Done | 30 mins
2026-02-18 | Ansella | Initialized Backend Folder Structure on Github and Created the PR | Done | 1 hr |  | Sprint 3 [Backend foundation and core feature implementation (Feb 18 - Mar 7, 2026)] : The team initialized the backend folder structure, set up FastAPI with a health check, implemented SR1 (user registration), SR2 (login + account lockout), SR3 (logout), SR4 (role-based access), SR8/SR9 (restaurant + menu endpoints), SR10 (menu validation), SR11/SR12 (restaurant ownership + category validation), cart data/repo/schemas, order schemas/repo, and pricing totals (SR32, SR34, SR35).
2026-02-18 | Ansella | Discussed Next Steps in M3 | Done | 1 hr
| Edgar | Discussed Next Steps in M3 | Done | 1 hr
| Yehezkiel | Discussed Next Steps in M3 | Done | 1 hr
| Yohanes | Discussed Next Steps in M3 | Done | 1 hr
2026-02-26 | Ansella | Discussed Next Steps and Project Structure of M3 | Done | 1 hr
| Edgar | Discussed Next Steps and Project Structure of M3 | Done | 1 hr
| Yehezkiel | Discussed Next Steps and Project Structure of M3 | Done | 1 hr
| Yohanes | Discussed Next Steps and Project Structure of M3 | Done | 1 hr
2026-02-26 | Ansella | Added basic FastAPI app and health check with unit test on Github | Done | 1 hr
2026-03-02 | Edgar | Started SR8 | Done | 2 hr
| Yehezkiel | Started SR32 | Done
2026-03-04 | Ansella | Started SR1 | Done
| Yehezkiel | Create Order and OrderItem schemas | Done
| Yehezkiel | Create Order and OrderItem Routes | Done | 1 hr
2026-03-06 | Ansella | Reported Personal Weekly Progress | Done | 1 hr
| Edgar | Reported Personal Weekly Progress | Done | 1 hr
| Yehezkiel | Reported Personal Weekly Progress | Done | 1 hr
| Yohanes | Reported Personal Weekly Progress | Done | 1 hr
2026-03-08 | Ansella | Reported Personal Weekly Progress | Done | 1 hr |  | Sprint 4 [Full feature completion, integration, and testing (Mar 8 - Mar 21, 2026)] : The team implemented SR5 (profile updates), SR6 (password reset), SR7 (login attempt logging), SR15–SR21 (search, filter, pagination, sorting, menu detail, recently viewed), SR28–SR31 (delivery status/details/assignment), SR33 (checkout re-validation), SR36/SR37/SR38/SR39 (order editing, input validation, delivery fees, stored totals), SR44–SR56 (payment flow, notifications, kitchen queue, driver assignment), and wrote unit + integration tests across all modules.
| Edgar | Reported Personal Weekly Progress | Done | 1 hr
| Yehezkiel | Reported Personal Weekly Progress | Done | 1 hr
| Yohanes | Reported Personal Weekly Progress | Done | 1 hr
2026-03-13 | Ansella | Reported Personal Weekly Progress | Done | 1 hr
| Edgar | Reported Personal Weekly Progress | Done | 1 hr
| Yehezkiel | Reported Personal Weekly Progress | Done | 1 hr
| Yohanes | Reported Personal Weekly Progress | Done | 1 hr
2026-03-14 | Ansella | Reported Personal Weekly Progress | Done | 1 hr
| Edgar | Reported Personal Weekly Progress | Done | 1 hr
| Yehezkiel | Reported Personal Weekly Progress | Done | 1 hr
| Yohanes | Reported Personal Weekly Progress | Done | 1 hr
2026-03-19 | Ansella | Reported Personal Weekly Progress | Done | 1 hr
| Edgar | Reported Personal Weekly Progress | Done | 1 hr
| Yehezkiel | Reported Personal Weekly Progress | Done | 1 hr
| Yohanes | Reported Personal Weekly Progress | Done | 1 hr
2026-03-21 | Ansella | Reported Personal Weekly Progress | Done | 1 hr
| Edgar | Reported Personal Weekly Progress | Done | 1 hr
| Yehezkiel | Reported Personal Weekly Progress | Done | 1 hr
| Yohanes | Reported Personal Weekly Progress | Done | 1 hr

## Team Members
Team Members
Add subjects or courses for the semester
Ansella
Edgar
Yehezkiel
Yohanes